## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Choose tablet vendor
research tablet features |  |  |  | 2 Days | bar: WEEK 1 M to WEEK 1 T
compare tablet pricing |  |  |  | 1 Day | bar: WEEK 1 W
confirm compatible operating system |  |  |  | 1 Day | bar: WEEK 1 R
create contracts and SoW for vendors |  |  |  | 2 Days | bar: WEEK 1 W to WEEK 1 R
Close a vendor |  |  |  | 1 Day | bar: WEEK 1 F
Milestone: Implement the Tablets
ship and receive tablets |  |  |  | 1 Week & 4 Days | bar: WEEK 2 M to WEEK 3 R
Schedule an electrician for the tablets' installation |  |  |  | 4 Days | bar: WEEK 3 F to WEEK 4 W
Integrate existing systems with the tablet |  |  |  | 3 Days | bar: WEEK 4 R to WEEK 5 M
Test the tablets |  |  |  | 1 Day | bar: WEEK 5 T
Create troubleshoot/support plan |  |  |  | 2 Days | bar: WEEK 5 M to WEEK 5 T
Milestone: Design & Configure the Tablets
Connect the S&S marketing team with Terrific Tablets for branding |  |  |  | 3 Days | bar: WEEK 5 W to WEEK 5 F
design the tablets to look like the hardcopy menu |  |  |  | 2 Days | bar: WEEK 6 M to WEEK 6 T
update menu items and coupon values |  |  |  | 1 Week | bar: WEEK 6 W to WEEK 7 T
implement a post-dining survey to assess customer satisfaction |  |  |  | 2 Days | bar: WEEK 7 W to WEEK 7 R
include images and descriptions for the food in the tablets |  |  |  | 2 Days | bar: WEEK 7 F to WEEK 8 M
enable GPS location services on each tablet |  |  |  | 2 Days | bar: WEEK 8 T to WEEK 8 W
create messaging about payment portal security to display on the tablets |  |  |  | 1 Day | bar: WEEK 8 R
establish security measures (employee permission & tablet locks) |  |  |  | 1 Day | bar: WEEK 8 F
connect the design and configurations with the tablets |  |  |  | 1 Day | bar: WEEK 9 M
test usability |  |  |  | 1 Day | bar: WEEK 9 T
Milestone: Train Staff
Prepare for staff training |  |  |  | 1 Week | bar: WEEK 9 W to WEEK 10 T
Schedule a training program for the GMs |  |  |  | 3 Days | bar: WEEK 10 W to WEEK 10 F
Schedule a training program for the staff |  |  |  | 3 Days | bar: WEEK 11 M to WEEK 11 W
Milestone: Launch
Invite friends and family to do a test run of the tablets (mimic a full service) |  |  |  | 2 Days | bar: WEEK 11 R to WEEK 11 F
Final Tests |  |  |  | 2 Days | bar: WEEK 12 M to WEEK 12 T

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Choose tablet vendor
research tablet features
compare tablet pricing
confirm compatible operating system
Create contracts and SoW for vendors
Close a vendor
Milestone: Implement the Tablets
Ship and receive tablets |  | 1 Week & 4 Days | 7 Days | 8 Days | 10 Days | H
Schedule an electrician for the tablets | Check with electrician on whether mornings or afternoons work better with their schedule, Notify GMs when their locations need to close for wiring | 4 Days | 4 Days | 5 Days | 7 Days | M
Install the tablets
Integrate existing systems with the tablet | Never Attemped | 3 Days | 1 Day | 2 Days | 5 Days | L
Test the tablets
Create troubleshoot/support plan
Milestone: Design & Configure the Tablets
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding
design the tablets to look like the hardcopy menu
update menu items and coupon values |  | 1 Week | 2 Days | 1 Week | 2 Weeks | H
implement a post-dining survey to assess customer satisfaction
include Images and descriptions of the food in the tablets.
Enable GPS location services on each tablet
Create messaging about payment portal security to display on the tablets
Establish security measures (employee permission, Tablet locks)
Connect the design and configurations with the tablets
Test the tablets
Milestone: Train Staff |  |  | 10 Days | 14 Days | 21 Days | H
Prepare for staff training | Attempted regularly | 1 Week | 1 Week | 1 Week & 3 Days | 2 Weeks | H
Schedule a training program for the GMs |  | 3 Days |  |  |  | H
Schedule a second training program for the staff at each location | Include payment security talking points in waitstaff training | 3 Days |  |  |  | M
Schedule staff meetings with the GM to discuss anything that could affect the waitstaff tips (get their buy-in)
Tasks:
Schedule an electrician for the tablets
Install the tablets
Train the staff for working with the tablets
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding
design the tablets to look like the hardcopy menu
upload the designs to the tablet
Create troubleshoot/support plan
Test the tablets
Integrate existing systems with the tablet
Allow promotion items on the tablet
implement a post-dining survey to assess customer satisfaction
Generate quotes and review costs
Create a launch day plan: staffing, troubleshooting, etc.
Create contracts and SoW for vendors
Determine network and hardware requirements
Establish security measures (employee permission, Tablet locks)
Set milestones for the success of the tablet rollout
include Images and descriptions of the food in the tablets.
Enable GPS location services on each tablet
Create messaging about payment portal security to display on the tablets
Include payment security talking points in waitstaff training
Schedule staff meetings with the GM to discuss anything that could affect the waitstaff tips (get their buy-in)
Invite friends and family to do a test run of the tablets (mimic a full service)
Schedule a training program for the GMs
Schedule a second training program for the staff at each location

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Average ticket time of 8 minutes for appetizers and 12-15 minutes for entrees. | 1. Are customers having a better dining experience with the tablets? | at least 90% customer satisfaction rates on surveys | FALSE
| One minutes checkout time | 2. Which customers are posting about their experiences on social media? | at least 30% of Customers who used the tablets would refer to friends | FALSE
| Have less than 5% technical issues reports by customers |  |  | FALSE
| 98% order accuracy |  |  | FALSE
| Average lobby wait time of under 10 minutes |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time of 8 minutes for appetizers and 12-15 minutes for entrees. | 1. Are customers having a better dining experience with the tablets? | at least 90% customer satisfaction rates on surveys | From 1 being very likely to 5 being would never, how likely are you to recommend our restaurant to a friend or colleague? | Scaled | Very likely to reccomend | Likely to recommend | Neutral | Not likely to recommend | Would never recommend
One minutes checkout time | 2. Which customers are posting about their experiences on social media? | at least 30% of Customers who used the tablets would refer to friends | From 1 being very satisfied to 5 being very dissatisfied, how satisfied were you from your experience using our tablets? | Scaled | Very satisfied | Somewhat satisfied | Neutral | Somewhat dissatisfied | Very dissatisfied
Have less than 5% technical issues reports by customers |  |  | What parts of using the tablet during your service did you find enjoyable/satissfying? | Open-ended | Open-Ended
98% order accuracy |  |  | What parts of using the tablet during your service did you find frustrating/dissatissfying? | Open-ended | Open Ended
Average lobby wait time of under 10 minutes |  |  | Did you enjoy using the tablet to order? | Yes/No | Yes | No
|  |  | Using tablets through the dining experience is better than receiving service from a person. | True/False | TRUE | FALSE
|  |  | How many times have you visited one of our restaurants? | Multiple choice | Never | Once | Twice | 3-4 Times | 5 or more times
|  |  | Were all of your orders accurately received? | Yes/No | Yes | No
|  |  | How many times have you used tablets to order food in restaurants before? | Multiple choice | Never | Once | Twice | 3-4 Times | 5 or more times
|  |  | Would you recommend our restaurant to a friend or colleague? | Yes/No | Yes | No

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
How to Develop a Successful POS System Implementation Plan | https://www.talech.com/blog/2020/05/07/resources-how-to-develop-a-successful-pos-system-implementation-plan/ | 2021-01-08 | Determine network and hardware requirements
Establish security measures (employee permission)
Set milestones for the success of the tablet rollout
All You Need to Know about INteractive Restaurant Menus | https://appinstitute.com/interactive-restaurant-menus/ | 2021-01-08 | include Images and descriptions of the food in the tablets.