## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | staff is well trained on the tablets | 76% of customers said that the waiter instructed them well
Customers | Went well | Good overall experience | 72% said their experience was great or good, 14% neutral
Customers | Went well | People felt confident in submitting payment through tablet | 88% of customers were between very confident or neutral
Customers | Needs improvement | Long wait for tables | 54% of customers waited more than 15 minutes for a table | Try to make shorter sitting or more tables
Customers | Needs improvement | Long wait for food | 42% of customers waited more than 20 minutes for their food | Check with kitchen
Customers | Needs improvement | kitchen mistakes | 28% of customers said the kitchen didnt prepare their orders correctly | Align with kitchen
Project team | Went well | All tablets are installed and working | Gilly (GM,North) and Alex (GM, Downtown)
Project team | Went well | Smooth ticket flow | Zane (Kitchen Manager, North)
Project team | Went well | surveys revealed meaningful data | Seydou (Consultant)
Project team | Needs improvement | no decrease in table turn time | Gilly (GM,North)
Project team | Needs improvement | Food orders got sent back | Larissa (Kitchen Manager, Downtown) | updates to kitchen operations
Project team | Needs improvement | few technical issues during pos integration | Seydou (Consultant) | update process manual
| Needs improvement | Lack of sync between FoH and BoH | Larissa (Kitchen Manager, Downtown) | develop a more comprehensive training session/break up training into 2 parts